## Forward Traceability
Requirements | Tests | Executions | Defects
SDB-44 - No error message is shown when try to add more than 10 characters into "Customer ID" field - 1 defect | SDB-38 - Verify if an error message is displayed when try to enter more than 10 characters into "Customer ID" field | Edit Customer - FAIL | SDB-44 - Backlog - No error message is shown when try to add more than 10 characters into "Customer ID" field
SDB-43 - An error message is displayed when try to edit the address of a customer - 1 defect | SDB-42 - Verify that you can edit the address of customer | Edit Customer - FAIL | SDB-43 - Backlog - An error message is displayed when try to edit the address of a customer
SDB-35 - No error message is displayed when try to add more than 25 characters in "City" field - 1 defect | SDB-26 - Verify if an error message is displayed when try to add more than 25 characters in "City" field | New Customer - FAIL | SDB-35 - Backlog - No error message is displayed when try to add more than 25 characters in "City" field
SDB-32 - Edit Customer form | SDB-33 - Verify if "Customer ID" field cannot be empty | Edit Customer - PASS | None
SDB-32 - Edit Customer form | SDB-34 - Verify if "Customer ID" field cannot contain alphabetic characters | Edit Customer - PASS | None
SDB-32 - Edit Customer form | SDB-36 - Verify if "Customer ID" field cannot contain special characters | Edit Customer - PASS | None
SDB-32 - Edit Customer form | SDB-37 - Verify if the first character of "Customer ID" field cannot have space | Edit Customer - PASS | None
SDB-32 - Edit Customer form - 1 defect | SDB-38 - Verify if an error message is displayed when try to enter more than 10 characters into "Customer ID" field | Edit Customer - FAIL | SDB-44 - Backlog - No error message is shown when try to add more than 10 characters into "Customer ID" field
SDB-32 - Edit Customer form | SDB-39 - Verify if an error message is displayed when enter an invalid Customer ID | Edit Customer - PASS | None
SDB-32 - Edit Customer form | SDB-40 - Verify if an error message is displayed when enter a Customer ID that is not associated with your manager account | Edit Customer - PASS | None
SDB-32 - Edit Customer form | SDB-41 - Verify that you can edit informations about a customer associated with your manager account | Edit Customer - PASS | None
SDB-32 - Edit Customer form - 1 defect | SDB-42 - Verify that you can edit the address of customer | Edit Customer - FAIL | SDB-43 - Backlog - An error message is displayed when try to edit the address of a customer
SDB-31 - 1.2 Edit Customer | None | None | None
SDB-27 - Add New Customer | SDB-28 - Verify if a manager can add a new customer | New Customer - PASS | None
SDB-27 - Add New Customer | SDB-29 - Verify if an error message is displayed when try to add a new customer without complete all the fields | New Customer - PASS | None
SDB-27 - Add New Customer | SDB-30 - Verify if an error message is displayed when try to add a new customer with the same email as an existing customer | New Customer - PASS | None
SDB-21 - Verify City field | SDB-22 - Verify if "City" field cannot be empty | New Customer - PASS | None
SDB-21 - Verify City field | SDB-23 - Verify if "City" field cannot be numeric | New Customer - PASS | None
SDB-21 - Verify City field | SDB-24 - Verify if "City" field cannot contain special characters | New Customer - PASS | None
SDB-21 - Verify City field | SDB-25 - Verify if the first character of the "City" field cannot have space | New Customer - PASS | None
SDB-21 - Verify City field - 1 defect | SDB-26 - Verify if an error message is displayed when try to add more than 25 characters in "City" field | New Customer - FAIL | SDB-35 - Backlog - No error message is displayed when try to add more than 25 characters in "City" field
SDB-20 - No error message is displayed when try to add more than 25 characters in "Name" field - 1 defect | SDB-19 - Verify if an error message is displayed when try to add more than 25 characters in "Name" field | New Customer - FAIL | SDB-20 - In Progress - No error message is displayed when try to add more than 25 characters in "Name" field
SDB-18 - No error message is shown when is reached the limit of 50 characters in "Address" field - 1 defect | SDB-17 - Verify if an error message is displayed when try to add more than 50 characters in "Address" field | New Customer - FAIL | SDB-18 - In Progress - No error message is shown when is reached the limit of 50 characters in "Address" field
SDB-13 - Verify Address field | SDB-14 - Verify if the "Address" field cannot be empty | New Customer - PASS | None
SDB-13 - Verify Address field | SDB-16 - Verify if the first character of the "Address" field cannot have space | New Customer - PASS | None
SDB-13 - Verify Address field - 1 defect | SDB-17 - Verify if an error message is displayed when try to add more than 50 characters in "Address" field | New Customer - FAIL | SDB-18 - In Progress - No error message is shown when is reached the limit of 50 characters in "Address" field
SDB-8 - Verify Name Field | SDB-9 - Verify if "Customer Name" field cannot be empty | New Customer - PASS | None
SDB-8 - Verify Name Field | SDB-10 - Verify if "Customer Name" field cannot be numeric | New Customer - PASS | None
SDB-8 - Verify Name Field | SDB-12 - Verify if the first character of the "Customer Name" field cannot have space | New Customer - PASS | None
SDB-8 - Verify Name Field - 1 defect | SDB-19 - Verify if an error message is displayed when try to add more than 25 characters in "Name" field | New Customer - FAIL | SDB-20 - In Progress - No error message is displayed when try to add more than 25 characters in "Name" field
SDB-7 - 1.1 New Customer | None | None | None
SDB-6 - 1.0 Manager Module - Guru99 Banking Project | None | None | None